## Sheet1
Time Spent | Date | To Do | Work Done
2 Hours | 30/07/2024 4pm - 6pm | Set up project | Created the Visual studio project with freeGlut set up. Worked out how to draw to the screen.
2 Hours | 03/08/2024 10am - 12pm | Work on setting up scene | Display the sky and ground on the screen. 3 ground points are random within a range. The sky has a gradient
2 Hours | 06/08/2024 12pm - 2pm | Draw Snowman | Create a function for drawing a circle. Draw 3 circles for the snow man body, plus 3 more circles for the eyes and noes
3 Hours | 19/08/2024 1pm - 4pm | Draw Snow | Created particle system for display the snow
2 Hours | 20/08/2024 3pm - 5pm | Add Features | Fixed scaling system and the snow disappearing. Display diagnostic data to the screen
| 21/08/2024 9am - | Add Features | Added the ability for the snowman to jumping following a parabolic curve based on the time.